## Slide 1
DATA & ANALYTICS
Executive Overview
Moving from SAS to Databricks
A brief outline of current state, ideal state, and the challenges to get there.
DATE
Aug 2026
Notes: Framing: this is a portfolio-level view of the SAS estate and what it takes to modernize it. 183 scripts inventoried and prioritized.

## Slide 2
PRIORITIZATION SUMMARY
Objective
Focus migration and modernization efforts on business-critical reports.
Priority was assigned from the script inventory — not by team, not by author, and not by ease of migration.
PRIORITY CRITERIA
Operational impact
Regulatory dependency
Data mart dependency
Utility
Evidence of active use
Modernizing the Credentialing Reporting Process
02
Notes: Objective slide. The point: we did not prioritize by convenience, we prioritized by business exposure.

## Slide 3
CURRENT STATE
People & Skills
01
Regulatory reporting is managed by a small group of maintainers, each owning their own domain. Two common skills across the group: SQL and SAS — the future state requires SQL and Python.
02
Maintainers are person1, person2, person3
03
Report maintainers have little time to dedicate to learning Databricks, Python and Git, or to experimentation and project management.
Modernizing the Credentialing Reporting Process
03
Notes: Current state, part one: who holds the knowledge and what they know. Fill in the maintainer names before presenting.

## Slide 4
CURRENT STATE
Tooling & Throughput
04
Scripts need constant maintenance due to shifting requirements, user error, and upstream changes.
05
The only ubiquitous AI tool is CoPilot.
06
A single script transfer takes anywhere from 2 days to 2 weeks, depending on system experience.
IMPLICATION
At current throughput, 50 high-priority scripts alone represent a multi-quarter effort, pushing the team up against Q4 2027 deadline.
Modernizing the Credentialing Reporting Process
04
Notes: Current state, part two: the mechanics. Two days to two weeks per script is the number to anchor on for capacity planning.

## Slide 5
IDEAL FUTURE STATE
Capability & Code Quality
SKILLS
All team members are comfortable with Databricks, Python, Git and GitHub. Most of the team is comfortable with SQL.
CODE
Scripts are simplified. Repetitive code is extracted into maintainable repositories that any team member can leverage easily.
QUALITY
Data quality checks and standards are built into the process rather than bolted on afterwards.
DOCUMENTATION
Reports are catalogued and documented via a well defined (and largely automated) process.
Modernizing the Credentialing Reporting Process
05
Notes: Target state, part one: capability and code quality. This is what 'done' looks like for the team and the codebase.

## Slide 6
IDEAL FUTURE STATE
Fidelity, AI & Self-Service
FIDELITY
Reports generated via SAS scripts are replicated exactly.
AI READY
Workflows are adjusted so developers use AI tools to manage the tedium of code writing — the developer checks code and focuses on testing.
ACCESS
Team members have access to powerful and modern AI tools.
SELF-SERVICE
A self-service tool allows business users to explore datasets on their own.
Modernizing the Credentialing Reporting Process
06
Notes: Target state, part two: fidelity of migrated reports, AI-ready workflows, and self-service for business users.

## Slide 7
GAP TO TARGET STATE
Challenges
DEVELOPER WORKFLOW
Copy and paste from CoPilot is tedious and overly laborious. AI workflows are the new normal.
CONNECTIVITY
Credentialing touches many different information systems, each with its own nuances. Databricks connections to legacy systems are still being developed — slowly.
LEARNING PYTHON
Learning a new language is not trivial. Finding time while sustaining current reporting obligations is deeply challenging.
LEARNING DATABRICKS
Databricks is a powerful, fast evolving tool. Understanding the peculiarities of how Kaiser has set up their instance(s) of Databricks is difficult. Moreover, core IT Updates to the Databricks system run ahead of clarifying information about changes to the system.
Modernizing the Credentialing Reporting Process
07
Notes: Challenges. Frame these as the gap between current and target state — most are solvable with time, tooling access, and clearer platform comms.

## Slide 8
Asks
WHO
Protected Time
Developers need time carve outs to upskill with respect to Databricks, Python and Git. Accommodations will be needed for regular reporting duties.
Management
Tooling access
Approve and facilitate modern AI tooling beyond CoPilot. Facilitate exploration of integrated development environments that connect to Databricks.
IT Procurement
Connections
Accelerate Databricks connections to key information systems and improve advance notice of platform changes.
IT
Archival mandate
Endorse dependency validation and retirement of low-priority assets before any migration work begins on them.
TBD
Modernizing the Credentialing Reporting Process
08
Notes: DRAFT ASKS — confirm these with the user before presenting. This is the decision slide: dedicated time, tooling access, and platform comms.

## Slide 9
BACKUP MATERIAL
Appendix
A — INVENTORY EXTRACT
Full script list with assigned priority, owner and last-run date.
inventory table
B — CRITERIA DEFINITIONS
How each of the five priority criteria was scored and weighted.
scoring rubric
C — COUNTS BY DOMAIN
Priority distribution across reporting domains and data marts.
chart placeholder
Modernizing the Credentialing Reporting Process
09
Notes: Appendix placeholder — drop the full inventory extract, criteria definitions, and per-domain counts here.

## Slide 10
APPENDIX D — THROUGHPUT MODEL
High Priority Timeline
SCRIPTS
50
AVG. PER SCRIPT
6 days
TOTAL EFFORT
300 days
ASSUMPTION
One developer, sequential
SCENARIO
Oct 26
Jan 27
Apr 27
Jul 27
Oct 27
Jan 28
Apr 28
Jul 28
Oct 28
Best case
2 days per script
Feb 2027 · 100 days
Base case
6 days per script
Dec 2027 · 300 days
Worst case
10 days per script
Sep 2028 · 500 days
Q4 2027 DEADLINE
Only the best case clears it. The base case lands roughly two months late — a second developer, or retiring low-priority assets to free capacity, closes the gap.
Modernizing the Credentialing Reporting Process
10
Notes: Single-developer, sequential estimate. 50 high-priority scripts at 6 business days each is 300 business days — about 14 months from an October start, landing December 2027, just past the Q4 2027 deadline. The 2-day and 10-day ends of the range bracket it: February 2027 at best, September 2028 at worst. Adding a second developer roughly halves the base case.

## Slide 11
APPENDIX E — INVENTORY
Script Breakdown by Priority
HIGH
50
27% of portfolio
MEDIUM
69
38% of portfolio
LOW
64
35% of portfolio
TOTAL SCRIPTS INVENTORIED
183
Modernizing the Credentialing Reporting Process
11
Notes: The headline numbers. 50 high, 69 medium, 64 low — 183 total. High priority is the near-term work.

## Slide 12
APPENDIX F — MIGRATION PRIORITY
Why This Order
HIGH PRIORITY CONCENTRATES ON
ETL pipelines
Regulatory reporting
Data mart refreshes
Shared utilities
THE REASONING
Regulatory reporting, recurring production processes, data mart refreshes, critical data feeds, and reusable automation components were prioritized because outages or defects would have broad business impact.
Modernizing the Credentialing Reporting Process
12
Notes: Rationale for the ranking. High priority clusters around things whose failure is visible outside the team.

## Slide 13
APPENDIX G — RECOMMENDATIONS
Low Priority Items
Many low-priority assets were explicitly marked as no longer needed, retiring, unknown, one-time analyses, or superseded reports. These should be validated for dependencies and considered for archival.
OPPORTUNITY
64
scripts that may not need migrating at all — retirement is cheaper than rewriting.
RECOMMENDED SEQUENCE
01
High-priority production assets
02
Medium-priority utilities and reports
03
Low-priority retirement candidates
Modernizing the Credentialing Reporting Process
13
Notes: Low priority items are an opportunity, not a backlog — a large share can be retired rather than migrated. Validate dependencies first.